## MM-User Stories
Sprint | As | I want to | So that | Type | Development From | Development To
1 | Developer | Requirements discussion | Can get review feedback | Development Event | 2020-06-01 | 2020-06-15 | Done
1 | Developer | Requirements review and finalization | Can get review feedback | Development Event | 2020-06-01 | 2020-06-15 | Done
1 | Developer | Set up initial database design for the system use | Can get review feedback | Development Event | 2020-06-01 | 2020-06-15 | Done
1 | Developer | Database review and updates | Can get review feedback | Development Event | 2020-06-01 | 2020-06-15 | Done
1 | Developer | Finalize the database | Can get review feedback | Development Event | 2020-06-01 | 2020-06-15 | Done
2 | Core User | have a homepage, has menu for navigations and to view features, news | this page will welcomes clients, gives them introduction about the system and features and show how to navigate the system | User Story | 2020-06-16 | 2020-06-30 | In Progress
2 | Developer | Set up system architecture | system is ready for development | Development Event | 2020-06-16 | 2020-06-30 | Done
2 | Developer | Set up bootstrap style | system is ready for development | Development Event | 2020-06-16 | 2020-06-30 | Done
2 | Developer | Set up and finalize the template for a basic UI with top menu, footer, home page, login and register screens (without functionality) and a completely functioning CRUD screen | Can get review feedback | Development Event | 2020-06-16 | 2020-06-30 | Done
2 | Developer | Demo the system developed | Can get review feedback | Development Event | 2020-06-16 | 2020-06-30 | Done
3 | MM System | enable authentication | Client Users, Core Users and Member users can only login to and use their relevant function | User Story | 2020-07-01 | 2020-07-15 | Done
3 | MM System | ensure that the clients cannot login to the system till they authenticated their emails and accepted terms and conditions | system integrity is maintained and emails misuse and fraud are avoided | User Story | 2020-07-01 | 2020-07-15 | Done
3 | Client User | ensure that the members cannot login to the system till they authenticated their emails and accepted terms and conditions | system integrity is maintained and emails misuse and fraud are avoided | User Story | 2020-07-01 | 2020-07-15 | Done
3 | MM System | ensure that the clients and their members' passwords are encrypted | system integrity is maintained in the event of possible data breach | User Story | 2020-07-01 | 2020-07-15 | Done
3 | MM System | allow users to open system without logging in every time | its easy for the users to login the user login cookies are still valid in their individual machines | User Story | 2020-07-01 | 2020-07-15 | Done
3 | MM System | Provide options for user to select common cities, states and countries throughout the system wherever needed. | a consistent look up data is provided to all clients | User Story | 2020-07-01 | 2020-07-15
3 | MM System | have clients, core members and members to have access to standard look up data: Default Address Types City States Country Currency Date Settings, Gender, Default Member Status, Time Formats, Time Zones, Titles, Default Qualifications, Default Address Types | A standardized data where applicable can be served throughout the system | User Story | 2020-07-01 | 2020-07-15 | Done
3 | MM System | be able to manage pages in the system | clients can choose pages to be the default landing page for their members | User Story | 2020-07-01 | 2020-07-15
4 | MM System | be able for users to add their addresses | clients and their members can create different type of contact details for them | User Story | 2020-07-16 | 2020-07-31
4 | MM System | Provide options for all lists to be exportable | users can export to different formats like excel, pdf | User Story | 2020-07-16 | 2020-07-31
4 | MM System | ensure that a standard, real time, user-friendly and modern form validation is used across the system | users find the forms and validation easy to understand, friendly and not confusing | User Story | 2020-07-16 | 2020-07-31
4 | Core User | have a pricing page where different subscription models are given | its easy for users to view, choose a subscription and to proceed to register | User Story | 2020-07-16 | 2020-07-31
4 | Core User | ensure that subscription plans are linked to the maximum number of contacts a client expects to have, each number will also have storage sizes allocated. | the system bills clients based on their member base and does not allow to create additional members without upgrading subscriptions | User Story | 2020-07-16 | 2020-07-31
4 | Core User | ensure that subscription plans have options to pay monthly, yearly and 2 years | the system bills the client as per their frequency preference | User Story | 2020-07-16 | 2020-07-31
4 | Core User | be able to update plans and prices | the existing subscriptions prices are updated for all clients but only in each client's next billing period. | User Story | 2020-07-16 | 2020-07-31
4 | Core User | Get notified when a client contact us | I am able to see the contact us record and respond to the query and assist the client | User Story | 2020-07-16 | 2020-07-31
5 | Client User | see a contact us and about us pages | I am able to contact the system admins and understand about the company | User Story | 2020-08-01 | 2020-08-15
5 | Client User | see a page that details all available features in the app | I can choose to proceed to register if I like the features | User Story | 2020-08-01 | 2020-08-15
5 | Client User | have a page or a view that allows me to register my company and a user, set up a subscription, A CRUD page for adding and managing my organization details: name, Time zone, Date and Time formats, Account owner details, contact email and addresses | I can start using the system | User Story | 2020-08-01 | 2020-08-15
5 | Client User | be able to set my communication preference | I get communication only based on my preference | User Story | 2020-08-01 | 2020-08-15
5 | Client User | Have a page in which I can set up roles for my users | I can have different type of users to handle different operations of my membership program | User Story | 2020-08-01 | 2020-08-15
5 | Client User | Have a page in which I can set up permissions for my roles | the roles have meaning and restrictions and powers to perform / not perform operations | User Story | 2020-08-01 | 2020-08-15
5 | Client User | be able to categorize my users by different designation | I am able to differentiate my users by their designation. | User Story | 2020-08-01 | 2020-08-15
5 | Client User | Have a page in which I can add additional users, assign them roles and passwords | I can have different type of users to handle different operations of my membership program | User Story | 2020-08-01 | 2020-08-15
5 | Client User | have a page or a view that allow me to login | I can manage my membership system, users and members | User Story | 2020-08-01 | 2020-08-15
5 | Client User | be able to change my password, reset passwords when forgot | I don’t get stuck not be able to use system | User Story | 2020-08-01 | 2020-08-15
5 | Client User | be able to change my subscription whenever possible | the new subscription can be enabled immediately and pricing is updated accurately | User Story | 2020-08-01 | 2020-08-15
5 | Client User | have a homepage, has menu for navigations and for members to view features, news | members can use this page to login to their profile. This will be my portal for my members to use my membership program, and to login and to register | User Story | 2020-08-01 | 2020-08-15
6 | Client User | have an overview page that summaries my account, summary of members, upcoming events, my website, link for accounts and billing | I get a summarized view of my program | User Story | 2020-08-16 | 2020-08-30
6 | Client User | a page that displays my account number, account type, contacts, administrators, storage, option to delete contacts and account, option to upgrade account | I can perform key functions from a single page | User Story | 2020-08-16 | 2020-08-30
6 | Client User | A CRUD and search page for contacts. | I can archive, delete contacts/ members in this page | User Story | 2020-08-16 | 2020-08-30
6 | Client User | have a CRUD page for Member Type. Each member type should also describe in detail the befits and features of the member type | I can group members into types e.g. Member – a contact with membership assigned (i.e. belongs to a particular membership level) Event attendee – anyone registered for at least one event Plain contact – a contact with no membership, or events associated with them | User Story | 2020-08-16 | 2020-08-30
6 | Client User | A CRUD page for grouping members | Members can be customized from different membership levels into member groups according to their interests or participation in committees or as per client's decision. For example le, I could create member groups such as "Board of Directors" or "Steering Committee". Member type can be grouped like Individual Members and Non individual members. | User Story | 2020-08-16 | 2020-08-30
6 | Client User | have a Security Check while members are registering to avoid automated addition of members in bulk | My application is stable. A captcha security check should be implemented while members try to add, to prevent automated addition of members | User Story | 2020-08-16 | 2020-08-30
6 | Client User | A CRUD page for member levels | I can assign levels to members based on their subscription E.g.: Regular membership, Premium | User Story | 2020-08-16 | 2020-08-30
6 | Client User | A CRUD page for Member Status | I can assign status for any members. Should have default values Applicant, Active and Suspended. I should be able to add additional look up values | User Story | 2020-08-16 | 2020-08-30
6 | Client User | be able to view the login and logout times of my users | to track for security and auditing purposes | User Story | 2020-08-16 | 2020-08-30
7 | Client User | be able to capture my bank account details | system can provide debit order options instead of my paying manually | User Story | 2020-09-01 | 2020-09-15
7 | Client User | be able to set up different subscription plans for members to select | members can choose the level they are comfortable with and choose payment frequency options | User Story | 2020-09-01 | 2020-09-15
7 | Client User | Manage which plans can change to which other plans | my subscription plans follow a logical pattern | User Story | 2020-09-01 | 2020-09-15
7 | MM System | send emails and reminders to clients when their member base and storage space is about to become full (75%,90% and 100%) | Clients can action to ensure their service is not interrupted | User Story | 2020-09-01 | 2020-09-15
7 | Client User | be able to collect information of affiliations of my members when the register, subscribe | for information purpose | User Story | 2020-09-01 | 2020-09-15
7 | Client User | know how a member was referred for membership | while a member registers, I can ask how he came to know about the membership and can use the information for marketing | User Story | 2020-09-01 | 2020-09-15
7 | Client User | be able to apply different taxes and tax policies for all my billings and transactions | correct taxes are applied to members | User Story | 2020-09-01 | 2020-09-15
7 | Client User | be able to create and assign status to members | I can view and action members by their status | User Story | 2020-09-01 | 2020-09-15
7 | Client User | be able to assign category to members | like Individual members or organization member | User Story | 2020-09-01 | 2020-09-15
7 | Client User | be able to group members into teams | I can view members like Board Members etc. | User Story | 2020-09-01 | 2020-09-15
7 | Client User | be able to group members into member types | I can group them like Non Member, Corporate Member, Student, Event Attendee, Presenter, Lifetime Member, Sponsor, Honorary Member, Foreign Member etc. | User Story | 2020-09-01 | 2020-09-15
8 | Client User | be able to categorize members by different marketing groups | I can target them for different events and courses | User Story | 2020-09-16 | 2020-09-30
8 | Client User | be able to categorize members by different profiles | I can target them for different events and courses | User Story | 2020-09-16 | 2020-09-30
8 | Client User | Set landing page for members | different member levels can be directed to different landing pages. | User Story | 2020-09-16 | 2020-09-30
8 | Client User | be able to generate rules for assigning member codes to my members | I can assign an uniform convention of codes assigned to my members | User Story | 2020-09-16 | 2020-09-30
8 | Member User | be able register as an organization member | as an organization I can enroll my associates to a membership program | User Story | 2020-09-16 | 2020-09-30
8 | Member User | as an organization member, be able add my associates | as an organization I can enroll my associates to a membership program | User Story | 2020-09-16 | 2020-09-30
8 | Member User | be able add my associates belonging to a branch of my organization | as a way to group my associates in the membership | User Story | 2020-09-16 | 2020-09-30
8 | Member User | be able to assign structure to my associates in the membership | as a way to group my associates in the membership | User Story | 2020-09-16 | 2020-09-30
8 | Member User | be able to as an organization member, be billed only to the organization and not to individual members | my associates do not need to pay individually | User Story | 2020-09-16 | 2020-09-30
8 | Member User | be able register as an individual member | even if I don’t belong to an organization I can be able to join a membership program | User Story | 2020-09-16 | 2020-09-30
8 | Member User | be able to select and pay for a membership level of my choice when I register | I can be able to choose the level of membership I prefer to | User Story | 2020-09-16 | 2020-09-30
8 | Member User | be able to capture my bank account details | system can provide debit order options to clients instead of my paying manually | User Story | 2020-09-16 | 2020-09-30
8 | Member User | be able to change my subscription whenever required | I can be able to choose my membership level as preferred, the billing should change to my next billing frequency. | User Story | 2020-09-16 | 2020-09-30
8 | Member User | be able to upload and retrieve files relevant for my membership | I can send proofs required for my membership and to be able to access it as required | User Story | 2020-09-16 | 2020-09-30
8 | Member User | be able to add my qualifications and upload relevant documents related to my qualifications | I can provide proofs of qualification as required by the program | User Story | 2020-09-16 | 2020-09-30
8 | Member User | be able to change my password, reset passwords when forgot | the new subscription can be enabled immediately and pricing is updated accurately | User Story | 2020-09-16 | 2020-09-30
9 | Client User | be able to set up simple and advanced events | members and public can attend; this will be a form of revenue for me and also manage CPDs of my members | User Story | 2020-10-01 | 2020-10-15
9 | Client User | be able to restrict access to events | I can design events to be public or only to a restricted list or set the event only for specific group of members | User Story | 2020-10-01 | 2020-10-15
9 | Client User | be able to track attendance of events | I can track the attendance to use in communication, CPDS and further events | User Story | 2020-10-01 | 2020-10-15
9 | Client User | be able to add items to event and assign costs to them | I can charge attendees for tickets, and can sell items in the event. | User Story | 2020-10-01 | 2020-10-15
9 | Client User | be able to assign my equipment and counts to an event | I can plan the required equipment to the events | User Story | 2020-10-01 | 2020-10-15
9 | Client User | be able to create and manage courses | Similar to events, I can assign CPD points to members and this should have all features of events | User Story | 2020-10-01 | 2020-10-15
9 | Client User | be able to create and manage meetings | Similar to events, I can assign CPD points to members and this should have all features of events and also should be able to save minutes of meetings | User Story | 2020-10-01 | 2020-10-15
9 | Client User | be able to assign roles to my users for events | I can assign specific users specific roles for the event | User Story | 2020-10-01 | 2020-10-15
9 | Client User | be able to tag entities like events and courses | they can be easily categorized by items of interest | User Story | 2020-10-01 | 2020-10-15
9 | Client User | be able to manage CPDs of all my members from a central place. | I can easily calculate the CPDs of my members | User Story | 2020-10-01 | 2020-10-15
9 | Client User | be able set up CPD target per member category | CPD targets for each member can be tracked based on the target | User Story | 2020-10-01 | 2020-10-15
9 | Client User | be able set up CPD target per member level | CPD targets for each member can be tracked based on the target | User Story | 2020-10-01 | 2020-10-15
9 | Client User | be able set up CPD target per member team | CPD targets for each member can be tracked based on the target | User Story | 2020-10-01 | 2020-10-15
9 | Client User | be able set up CPD target per member type | CPD targets for each member can be tracked based on the target | User Story | 2020-10-01 | 2020-10-15
9 | Client User | be able to manage equipment and their counts in my organization | I can use this information during event setups | User Story | 2020-10-01 | 2020-10-15
9 | Client User | be able to accept or reject a membership request | if a membership request does not suit my membership requirements | User Story | 2020-10-01 | 2020-10-15
10 | Client User | be able to view the login and logout times of my members | to track for security and auditing purposes | User Story | 2020-10-15 | 2020-10-30
10 | Client User | be able to select different communication types | I can choose communication type of my preference | User Story | 2020-10-15 | 2020-10-30
10 | Client User | be able to send communications and reminders to my members for all billing | that members are informed in advance about payments they need to make. This will also serve as a mechanism to track who are behind payments. | User Story | 2020-10-15 | 2020-10-30
10 | Client User | be able to manage different email templates | I can choose different templates for communication with my members and users | User Story | 2020-10-15 | 2020-10-30
10 | Client User | be able to categorize my email templates | I can choose if a template is for greetings, billing, reminders, events etc. | User Story | 2020-10-15 | 2020-10-30
10 | Client User | be able to communicate events, reminders to people who are target audience | the users get notified and get communication regularly | User Story | 2020-10-15 | 2020-10-30
10 | Client User | be able to set email CC rules | my users are automatically copied for different categories of emails sent by the system | User Story | 2020-10-15 | 2020-10-30
10 | Client User | be able to accept donations | members or public can be able to donate to my organization | User Story | 2020-10-15 | 2020-10-30
10 | Client User | be able to create invoices for members and relate them to multiple items | I can charge members | User Story | 2020-10-15 | 2020-10-30
10 | Client User | be able to automatically create invoices to members | I don’t need to do this manually, but system assist me to do this. | User Story | 2020-10-15 | 2020-10-30
10 | Client User | be able to create invoice numbers automatically based on the last invoice number | I don’t need to do this manually, but system assist me to do this. | User Story | 2020-10-15 | 2020-10-30
10 | Client User | be able to manage different invoice statuses | I can categorize if an invoice is sent, pending, paid etc. | User Story | 2020-10-15 | 2020-10-30
10 | Member User | be able to follow a promotion | Apply and benefit for the features given in the promotion | User Story | 2020-10-15 | 2020-10-30
10 | Client User | be able to add multiple payment options and gateways | members can use their preferred payment gateways to make payments | User Story | 2020-10-15 | 2020-10-30
10 | Client User | be able to create and run promotions | members can choose promotions for various activities like registration , events | User Story | 2020-10-15 | 2020-10-30
10 | Client User | be able to refund members | if the need arises for refunds, this can be handled from the system | User Story | 2020-10-15 | 2020-10-30
10 | Member User | be able to register to events, courses and meetings, I should be able to update my responses | I can confirm my response to events | User Story | 2020-10-15 | 2020-10-30
11 | Client User | have a dashboard page to view how my membership system is performing. | Using charts showing all the standard metrics , I would be able to track my membership program | User Story | 2020-11-01 | 2020-11-15
11 | Client User | have a good list of reports | it will help me to view key data related to my program | User Story | 2020-11-01 | 2020-11-15
11 | Client User | be able to create cards and assign to members | my members can have cards that can be printed | User Story | 2020-11-01 | 2020-11-15
11 | Core User | be able to view the login and logout times of my users | to track for security and auditing purposes | User Story | 2020-11-01 | 2020-11-15
11 | Core User | be able to capture my bank account details | Clients can choose to pay to the provided banking details | User Story | 2020-11-01 | 2020-11-15
11 | Core User | be able to manage all my billing to all the clients from a central place | I don't need complex mechanism to track invoices and billing related to various items | User Story | 2020-11-01 | 2020-11-15
11 | Core User | Provide default communication types to all users | Clients can start using standard communication types and customize as per their preference | User Story | 2020-11-01 | 2020-11-15
11 | Client User | be able to add custom fields for my members and events | the system can be adapted to my business | User Story | 2020-11-01 | 2020-11-15
11 | Core User | Have a page in which I can set up roles for my users | I can have different type of users to handle different operations of my system | User Story | 2020-11-01 | 2020-11-15
11 | Core User | have a dashboard page to view how my business is performing. | Using charts showing all the standard metrics , I would be able to track my business performance and various other metrics | User Story | 2020-11-01 | 2020-11-15
11 | Core User | have a good list of reports | it will help me to view key data related to my business | User Story | 2020-11-01 | 2020-11-15
12 | Developer | Testing,fixes and Deployment | the system is ready for produciton | Development Event | 2020-11-15 | 2020-11-30